## RACI — Full Tracker
EasyChef Pro — RACI Confirmation Tracker ¦ Source: Adam's GTM Project Tracker (exact)
All task data is taken EXACTLY from Adam's tracker. RACI columns added for confirmation process. R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed ¦ Yellow cells = owner must confirm. Flag column = gaps that must be resolved before Monday.
Task ID | Task Name | Category | Priority | Status | Owner (Adam's Sheet) | Start Date (Adam's Sheet) | ETA (Adam's Sheet) | Dependencies (Adam's Sheet) | Notes / Description (Adam's Sheet) | Taylor (IC / A) | Steve (Ops) | Adam (Planning) | Mary (Content) | JR (Flows) | Hammad/Dev (Logistics) | Searah (Social Ops) | Sadee (Support/Beta) | Confirmed? ⬅ Owner fills YES/NO/PARTIAL | ICS Flags (Gaps from Adam's sheet)
▶ MARKETING STRATEGY
T-001 | ICP Research | Marketing Strategy | High | Started | Adam |  |  |  | Define ideal customer profile: demographics, psychographics, pain points | A | I | R | I | I | I
T-002 | Competitive Analysis | Marketing Strategy | High | Started | Adam |  |  |  | Map direct & indirect competitors; feature/pricing/positioning matrix | A | I | R | I | I | I
T-003 | Positioning Strategy | Marketing Strategy | High | Started | Adam |  |  | T-001, T-002 | Craft market position statement; own-able whitespace | A | I | R | I | I | I
T-004 | Differentiation | Marketing Strategy | High | Started | Adam |  |  | T-003 | Define key differentiators vs. alternatives | A | I | R | I | I | I
T-005 | Brand Messaging Framework / Tagline | Marketing Strategy | High | Started | Adam |  |  | T-003 | Value prop, tone of voice, messaging pillars, tagline | A | I | R | I | I | I | I
T-006 | Pricing | Marketing Strategy | High | Started | Adam |  |  | T-001, T-002 | Freemium vs. paid tiers; willingness-to-pay research | A | I | R | I | I | I
T-007 | Behavioural Economics Analysis | Marketing Strategy | Medium | Started | Adam |  |  | T-001 | Anchoring, loss aversion, social proof levers to embed in UX & copy | A | I | R | I | I | I
T-008 | Go-to-Market (GTM) Strategy | Marketing Strategy | High | Started | Adam |  |  | T-003, T-006 | Master launch plan: channels, sequencing, budget allocation, KPIs | A | I | R | I | I | I | I
T-009 | Customer Journey Mapping (Full-Funnel) | Marketing Strategy | High | Started | Adam |  |  | T-001, T-003 | Awareness > activation > retention > referral journey | A | I | R | I | I | I | I
▶ BRAND
T-010 | Brand Guidelines & Visual Identity | Brand | High | Not Started | Adam |  |  | T-005 | Logo, colour palette, typography, imagery style, icon system | A | I | R | I | I | I | I
▶ CONTENT - WEBSITE
T-011 | Website Content (all pages) | Content - Website | High | Not Started | Adam |  |  | T-005, T-010 | Homepage, features, pricing, about, blog index | A | I | R | I | I | I
T-012 | Website Pre-Launch Content | Content - Website | High | Started | Mary |  |  | T-011 | Coming-soon page, waitlist CTA, teaser messaging | A | I | I | R | I | I
T-013 | Video Demo / Explainer Content | Content - Website | High | Not Started | Adam + |  |  | T-005, T-010 | 60-90s product demo for homepage and social ads | A | I | R | I | I | I |  |  |  | ⚠️ 'Adam +' — who is the '+'? Must be named before task can start.
T-014 | App Store Listing (ASO Copy) | Content - Website | High | Not Started | Hammad |  |  | T-005 | Title, subtitle, description, keywords; App Store & Google Play | A | I | I | I | I | R
T-015 | Blog / Content Strategy | Content - Website | Medium | Not Started | Mary + Adam |  |  | T-003 | Editorial calendar; SEO-led topics that build authority | A | I | R | R | I | I
T-016 | PR / Press Outreach Strategy | Content - Website | Medium | Not Started | Mary + Adam |  |  | T-008 | Target media list, story angles, press kit | A | I | R | R | I | I
▶ DIGITAL MARKETING
T-017 | Search Engine Optimization (SEO) | Digital Marketing | High | Not Started | Adam |  |  | T-011 | On-page, technical SEO, backlink strategy | A | I | R | I | I | I
T-018 | Paid Search (SEM / Google Ads) | Digital Marketing | High | Not Started | Adam + |  |  | T-008 | Keyword strategy, ad copy, landing pages, bidding | A | I | R | I | I | I |  |  |  | ⚠️ 'Adam +' — who is the '+'? Must be named before task can start.
T-019 | App Store Ads (Apple Search Ads / UAC) | Digital Marketing | High | Not Started | Adam + |  |  | T-014, T-008 | ASA and Google UAC campaign setup | A | I | R | I | I | I |  |  |  | ⚠️ 'Adam +' — who is the '+'? Must be named before task can start.
T-020 | Influencer Marketing | Digital Marketing | Medium | Not Started | JR |  |  | T-008, T-010 | Identify micro/macro food creators; brief and contract | A | I | I | I | R | I | C
T-021 | Retargeting Campaign Setup | Digital Marketing | High | Not Started | Adam + |  |  | T-018 | Pixel setup, audience lists, retargeting ad creative briefs | A | I | R | I | I | I |  |  |  | ⚠️ 'Adam +' — who is the '+'? Must be named before task can start.
▶ SOCIAL MEDIA MARKETING
T-022 | Social Media Campaign Design | Social Media Marketing | High | Not Started | Adam + Searah |  |  | T-008, T-010 | Platform strategy (IG, TikTok, Pinterest); content calendar | A | I | R | I | I | I | R |  |  | ✓ Resolved — Searah assigned as execution lead
T-023 | Advertising Budget & User Journey Mapping | Social Media Marketing | High | Not Started | Taylor + Steve + Adam |  |  | T-008, T-009 | Paid social budget split; map ad touchpoints to funnel stages | A/R | R | R | I | I | I | I
T-024 | Social Media Creatives | Social Media Marketing | High | Not Started | Adam + Searah |  |  | T-010, T-022 | Static, carousel, Reel/TikTok creative assets | A | I | R | I | I | I | R |  |  | ✓ Resolved — Searah assigned as execution lead
▶ EMAIL MARKETING
T-025 | Email Marketing Campaign | Email Marketing | High | Not Started | JR + Mary |  |  | T-008 | Broadcast campaigns: promos, feature announcements, newsletters | A | I | I | R | R | I |  | I
T-026 | Onboarding Email Sequence | Email Marketing | High | Not Started | JR |  |  | T-009, T-025 | Welcome > activation drip (Day 0-14); drive first recipe use | A | I | I | I | R | I
▶ PRODUCT MARKETING
T-027 | Product-Led Onboarding | Product Marketing | High | Started | Adam + Hammad + Taylor + Steve |  |  | T-009 | In-app onboarding flows that drive time-to-value | A/R | R | R | I | I | R |  | I |  | ⚠️ 3 owners listed — ICS rule: one R per task. Clarify lead.
T-028 | User Story Cards | Product Marketing | High | Started | Adam |  |  | T-001 | Backlog of user stories prioritised for launch sprint | A | I | R | I | I | I
T-029 | Cold Start Tactics | Product Marketing | High | Started | Adam |  |  | T-008 | Bootstrapping initial users: communities, waitlist, beta program | A | I | R | I | I | I
T-030 | Referral Program Design | Product Marketing | High | Not Started | JR |  |  | T-029 | Incentive structure, referral mechanics, tracking | A | I | I | I | R | I
T-031 | In-App Notification Strategy | Product Marketing | Medium | Not Started | Hammad + Adam |  |  | T-027 | Push / in-app messages to drive retention and feature discovery | A | I | R | I | I | R
T-032 | Feature Launch Announcement Strategy | Product Marketing | Medium | Not Started | All |  |  | T-005 | Template and process for communicating new features post-launch | A/R | R | R | R | R | R | I | I |  | ⚠️ 'All' = zero accountability. Must assign single R before Monday.
▶ DATA SCIENCE
T-033 | A/B Testing Framework Setup | Data Science | High | Not Started | Hammad + Adam |  |  |  | Define test methodology, tooling, statistical significance thresholds | A | I | R | I | I | R
T-034 | Funnel Analysis & Conversion Tracking | Data Science | High | Not Started | Hammad + Adam |  |  | T-027 | Event tracking; map funnel from install to paid; identify drop-offs | A | I | R | I | I | R
T-035 | App Analytics | Data Science | High | Not Started | Hammad + Adam |  |  | T-034 | DAU/MAU, retention curves, feature engagement; dashboard setup | A | I | R | I | I | R
T-036 | Website Analytics | Data Science | High | Not Started | Hammad + Adam |  |  |  | GA4 / Mixpanel setup; goals, events, attribution model | A | I | R | I | I | R
T-037 | Retention & Churn Analysis Framework | Data Science | Medium | Not Started | Hammad + Adam |  |  | T-035 | Cohort retention analysis; churn signals; lifecycle segmentation | A | I | R | I | I | R
▶ PARTNERSHIPS
T-038 | Food Creator / Influencer Partnership Program | Partnerships | Medium | Not Started | TBD |  |  | T-020 | Long-term ambassador tiers, content obligations, compensation model | A | I | I | I | I | I |  | I |  | ⚠️ NO OWNER ASSIGNED — must be resolved before Monday
T-039 | Customer Success Infrastructure | Launch Ops | High | Ready to deploy | Sadee |  | May 11 |  | support@easyChefPro.com — Sadee owns frontline. Zendesk setup. Boho Beach Hut team on standby for surge. Threshold: 30-50 tickets/week before escalation. | A | I | I | I | I | I | I | R
T-040 | Alpha & Beta Feedback Loop | Launch Ops | High | Ready to set up | Adam / Sadee |  | May 11 | T-039 | Separate feedback email channel. Bugs → Hammad. PMF signals → Adam. User language → Mary. Sadee routes and tracks. | A | I | C | C | I | I | I | R

## Summary (Fixed)
Summary — Preserved from Adam's Sheet ¦ Formulas fixed
Tasks by Category
Category | Total Tasks | % of Backlog | Legend
Brand | 1 | 2.632%
Content - Website | 6 | 15.79%
Data Science | 5 | 13.16%
Digital Marketing | 5 | 13.16%
Email Marketing | 2 | 5.263%
Marketing Strategy | 9 | 23.68%
Partnerships | 1 | 2.632%
Product Marketing | 6 | 15.79%
Social Media Marketing | 3 | 7.895%
TOTAL | 38 | 100.0%
Status Key
Not Started
In Progress
In Review
Completed
Blocked
Priority Key
High
Medium
Low

## Personal Commitment Cards
Personal Commitment Cards — Built from Adam's Exact Owner Assignments
Each person reviews their tasks only. Fill Column E (commit yes/no/partial), Column F (your honest date), Column G (what you need from others). Return to Steve by Friday EOD.
Task ID | Task Name (from Adam's sheet) | Adam's Owner Field | Your RACI Role | Can You Commit? YES / NO / PARTIAL | Your Realistic Date (honest estimate) | What Do You Need From Others?
TAYLOR — Incident Commander (Accountable on all tasks)
T-001 | ICP Research | Adam | A
T-002 | Competitive Analysis | Adam | A
T-003 | Positioning Strategy | Adam | A
T-004 | Differentiation | Adam | A
T-005 | Brand Messaging Framework / Tagline | Adam | A
T-006 | Pricing | Adam | A
T-007 | Behavioural Economics Analysis | Adam | A
T-008 | Go-to-Market (GTM) Strategy | Adam | A
T-009 | Customer Journey Mapping (Full-Funnel) | Adam | A
T-010 | Brand Guidelines & Visual Identity | Adam | A
T-011 | Website Content (all pages) | Adam | A
T-012 | Website Pre-Launch Content | Mary | A
T-013 | Video Demo / Explainer Content | Adam + | A
T-014 | App Store Listing (ASO Copy) | Hammad | A
T-015 | Blog / Content Strategy | Mary + Adam | A
T-016 | PR / Press Outreach Strategy | Mary + Adam | A
T-017 | Search Engine Optimization (SEO) | Adam | A
T-018 | Paid Search (SEM / Google Ads) | Adam + | A
T-019 | App Store Ads (Apple Search Ads / UAC) | Adam + | A
T-020 | Influencer Marketing | JR | A
T-021 | Retargeting Campaign Setup | Adam + | A
T-022 | Social Media Campaign Design | Adam + | R — Searah
T-023 | Advertising Budget & User Journey Mapping | Taylor + Steve + Adam | A | Yes | Ontime | Monday at 11AM ET (8AM PT) to discuss the roadmap, the content that Mary will deliver by EOD Friday, and our finalized positioning strategy.
T-024 | Social Media Creatives | Adam + | R — Searah
T-025 | Email Marketing Campaign | JR + Mary | A
T-026 | Onboarding Email Sequence | JR | A
T-027 | Product-Led Onboarding | Adam + Hammad + Taylor + Steve | A | Yes | Ontime | Monday at 11AM ET (8AM PT) to discuss the roadmap, the content that Mary will deliver by EOD Friday, and our finalized positioning strategy.
T-028 | User Story Cards | Adam | A
T-029 | Cold Start Tactics | Adam | A
T-030 | Referral Program Design | JR | A
T-031 | In-App Notification Strategy | Hammad + Adam | A
T-032 | Feature Launch Announcement Strategy | All | A
T-033 | A/B Testing Framework Setup | Hammad + Adam | A
T-034 | Funnel Analysis & Conversion Tracking | Hammad + Adam | A
T-035 | App Analytics | Hammad + Adam | A
T-036 | Website Analytics | Hammad + Adam | A
T-037 | Retention & Churn Analysis Framework | Hammad + Adam | A
T-038 | Food Creator / Influencer Partnership Program | TBD | A
STEVE — Operations (from Adam's sheet: T-023, T-027, T-032)
T-023 | Advertising Budget & User Journey Mapping | Taylor + Steve + Adam | R |  |  | Monday at 11AM ET (8AM PT) to discuss the roadmap, the content that Mary will deliver by EOD Friday, and our finalized positioning strategy.
T-027 | Product-Led Onboarding | Adam + Hammad + Taylor + Steve | R |  |  | Monday at 11AM ET (8AM PT) to discuss the roadmap, the content that Mary will deliver by EOD Friday, and our finalized positioning strategy.
T-032 | Feature Launch Announcement Strategy | All | R
ADAM — Planning (all tasks listed as Adam owner)
T-001 | ICP Research | Adam | R
T-002 | Competitive Analysis | Adam | R
T-003 | Positioning Strategy | Adam | R
T-004 | Differentiation | Adam | R
T-005 | Brand Messaging Framework / Tagline | Adam | R
T-006 | Pricing | Adam | R
T-007 | Behavioural Economics Analysis | Adam | R
T-008 | Go-to-Market (GTM) Strategy | Adam | R
T-009 | Customer Journey Mapping (Full-Funnel) | Adam | R
T-010 | Brand Guidelines & Visual Identity | Adam | R |  |  |  | Recommended: Hammad = R (builds it). Adam = R (strategy). Taylor = A (accountable). Steve = I. Taylor confirmed YES for Monday
T-011 | Website Content (all pages) | Adam | R
T-013 | Video Demo / Explainer Content | Adam + | R
T-015 | Blog / Content Strategy | Mary + Adam | R
T-016 | PR / Press Outreach Strategy | Mary + Adam | R
T-017 | Search Engine Optimization (SEO) | Adam | R
T-018 | Paid Search (SEM / Google Ads) | Adam + | R
T-019 | App Store Ads (Apple Search Ads / UAC) | Adam + | R
T-021 | Retargeting Campaign Setup | Adam + | R
T-022 | Social Media Campaign Design | Adam + | R — Searah
T-023 | Advertising Budget & User Journey Mapping | Taylor + Steve + Adam | R |  |  | Monday at 11AM ET (8AM PT) to discuss the roadmap, the content that Mary will deliver by EOD Friday, and our finalized positioning strategy.
T-024 | Social Media Creatives | Adam + | R — Searah
T-027 | Product-Led Onboarding | Adam + Hammad + Taylor + Steve | R |  |  | Monday at 11AM ET (8AM PT) to discuss the roadmap, the content that Mary will deliver by EOD Friday, and our finalized positioning strategy.
T-028 | User Story Cards | Adam | R
T-029 | Cold Start Tactics | Adam | R
T-031 | In-App Notification Strategy | Hammad + Adam | R
T-033 | A/B Testing Framework Setup | Hammad + Adam | R
T-034 | Funnel Analysis & Conversion Tracking | Hammad + Adam | R
T-035 | App Analytics | Hammad + Adam | R
T-036 | Website Analytics | Hammad + Adam | R
T-037 | Retention & Churn Analysis Framework | Hammad + Adam | R
MARY — Content Lead (T-012, T-015, T-016, T-025)
T-012 | Website Pre-Launch Content | Mary | R
T-015 | Blog / Content Strategy | Mary + Adam | R
T-016 | PR / Press Outreach Strategy | Mary + Adam | R
T-025 | Email Marketing Campaign | JR + Mary | R
JR — Flows & Influencer Lead (T-020, T-025, T-026, T-030, T-038)
T-020 | Influencer Marketing | JR | R
T-025 | Email Marketing Campaign | JR + Mary | R
T-026 | Onboarding Email Sequence | JR | R
T-030 | Referral Program Design | JR | R
HAMMAD / DEV TEAM — Logistics (T-014, T-027, T-031–T-037)
T-014 | App Store Listing (ASO Copy) | Hammad | R
T-027 | Product-Led Onboarding | Adam + Hammad + Taylor + Steve | R |  |  | Monday at 11AM ET (8AM PT) to discuss the roadmap, the content that Mary will deliver by EOD Friday, and our finalized positioning strategy. | Recommended: Hammad = R (builds it). Adam = R (strategy). Taylor = A (accountable). Steve = I. Taylor confirmed YES for Monday.
T-031 | In-App Notification Strategy | Hammad + Adam | R
T-033 | A/B Testing Framework Setup | Hammad + Adam | R
T-034 | Funnel Analysis & Conversion Tracking | Hammad + Adam | R
T-035 | App Analytics | Hammad + Adam | R
T-036 | Website Analytics | Hammad + Adam | R
T-037 | Retention & Churn Analysis Framework | Hammad + Adam | R
⚠️ UNASSIGNED / TBD — Must be resolved before Monday
T-013 | Video Demo / Explainer Content | Adam + | ❓ UNASSIGNED |  |  |  | Who is doing video production? Videographer, agency, or AI-assisted? Must be named before T-005/T-010 complete.
T-018 | Paid Search (SEM / Google Ads) | Adam + | ❓ UNASSIGNED | Taylor- yes |  |  | Agency, freelancer, or internal? Must be named this week. Google Ads setup needs 2–3 weeks before launch spend ramps.
T-019 | App Store Ads (Apple Search Ads / UAC) | Adam + | ❓ UNASSIGNED |  |  |  | May be same operator as T-018 (SEM). Confirm and assign. Depends on T-014 App Store Listing (Hammad).
T-021 | Retargeting Campaign Setup | Adam + | ❓ UNASSIGNED | Taylor - yes ? |  |  | Likely same person as T-018 (SEM). Name the paid media operator once for both tasks.
T-022 | Social Media Campaign Design | Adam + | R — Searah |  |  |  | Mary can own content side. Name the '+' for creative production. Could be same designer as T-010/T-024.
T-024 | Social Media Creatives | Adam + | R — Searah |  |  |  | Designer or agency must be named. This task is doubly blocked: needs T-010 done AND needs named creative person.
T-032 | Feature Launch Announcement Strategy | All | ❓ UNASSIGNED | Stratagy Adam, Jr, Mary |  |  | Recommended: Mary owns copy. Adam owns strategy. Single R = Adam. Mary = C. Post-launch this must ship with first feature release
T-038 | Food Creator / Influencer Partnership Program | TBD | ❓ UNASSIGNED | Adam and Searah? |  |  | Recommended: Assign to JR. JR already owns T-020 (Influencer Marketing). Logical extension of same workstream.
SEARAH — Marketing Operations Associate (Social Execution)
T-022 | Social Media Campaign Design | Adam + Searah | R |  |  | Get access to all platforms + meet designer this week (W1)
T-024 | Social Media Creatives | Adam + Searah | R |  |  | Get access to all platforms + meet designer this week (W1)
SADEE — PA / Support & Beta Operations
T-039 | Customer Success Infrastructure | Sadee | R |  | Before May 11 | Zendesk setup + support@easyChefPro.com live before May 11
T-040 | Alpha & Beta Feedback Loop | Adam / Sadee | R |  | Before May 11 | Route bugs → Hammad, PMF → Adam, language → Mary

## ICS Dashboard — Steve
EasyChef Pro — ICS Operations Dashboard ¦ Steve owns this. Taylor reviews Monday.
⚠️ ACCOUNTABILITY GAPS — Derived directly from Adam's owner field
Task ID | Task Name | Adam's Owner (exact) | Gap Type | Impact | Steve's Action Required
T-038 | Food Creator / Influencer Partnership | TBD | No owner assigned | Influencer pipeline has no lead — blocks T-020 downstream | Assign owner before Monday. Likely JR based on T-020 ownership.
T-032 | Feature Launch Announcement Strategy | All | 'All' = zero accountability | When this fails everyone looks at someone else | Assign single R. Recommend Mary for copy, Adam for strategy.
T-027 | Product-Led Onboarding | Adam + Hammad + Taylor + Steve | 4 owners = accountability gap | Critical path item. <3 min Aha must ship on time. | Assign single R. Hammad owns build. Adam owns strategy. Taylor reviews.
T-023 | Advertising Budget & User Journey | Taylor + Steve + Adam | 3 owners = accountability gap | Budget decisions need one accountable person | Steve owns as Ops lead. Adam consults on strategy. Taylor approves.
T-013 | Video Demo / Explainer Content | Adam + | 'Adam +' — '+' is unnamed | Production cannot start without named owner | Name the '+'. Who is doing video production?
T-018 | Paid Search / Google Ads | Adam + | 'Adam +' — '+' is unnamed | SEM execution needs a named operator | Name the '+'. Is this an agency, freelancer, or internal?
T-019 | App Store Ads (ASA / UAC) | Adam + | 'Adam +' — '+' is unnamed | ASO ads need dedicated operator | Name the '+' before campaign briefing starts.
T-021 | Retargeting Campaign Setup | Adam + | 'Adam +' — '+' is unnamed | Pixel and audience setup needs dedicated operator | Name the '+'. Confirm who owns paid media execution.
T-022 | Social Media Campaign Design | Adam + | 'Adam +' — '+' is unnamed | Content calendar and platform strategy need named lead | Mary can own content side. Name the '+' for creative production.
T-024 | Social Media Creatives | Adam + | 'Adam +' — '+' is unnamed | Creative assets need named designer or agency | Name the '+'. Is this a designer, agency, or internal resource?
📅 DATE GAPS — Every Start Date and ETA is blank in Adam's sheet. These must be locked Monday.
38 tasks. 0 start dates. 0 ETAs. Adam's roadmap Gantt has the locked dates — Steve's first job is to populate the Start Date and ETA columns in the RACI tracker from Adam's Gantt tab before Monday's meeting.
🚀 KEY MILESTONES — Steve confirms or flags before Monday
Milestone | Target Date (from Adam's roadmap) | Owner (Adam's sheet) | Confirmed? (yes/no) | What Blocks It | Steve's Notes
Beta Launch | May 11 | Hammad + Adam + Taylor + Steve (T-027) |  | App stable. <3 min Aha confirmed. Load capacity confirmed.
Beta Data Checkpoint / Kill Criteria | June 8 | Adam + Steve |  | Beta running. KPIs defined. PMF thresholds agreed by all.
Social Content Goes Live | Week 4 pre-launch | Adam + |  | Beta outcomes in hand. Brand guidelines (T-010) done. Creatives (T-024) done.
Marketing Launch | July 1 | All |  | Every upstream dependency confirmed. No placeholder tasks remaining.
Brand Guidelines Complete | ASAP — Not Started | Adam (T-010) |  | Designer assigned and briefed. T-011, T-013, T-022, T-024 all blocked until done.
Content Calendar Delivered | Friday EOD this week | Mary (T-012) |  | Already in progress. Committed.

## How To Use
HOW TO USE THIS FILE — Read first
ACCURACY NOTE
Every task in this file is taken EXACTLY from Adam's GTM Project Tracker. Task IDs, names, categories, priorities, statuses, owners, dependencies, and notes have not been changed.
The RACI columns (Taylor, Steve, Adam, Mary, JR, Hammad/Dev) are derived directly from Adam's Owner field — not invented or assumed.
The ICS Flags column identifies gaps that exist IN Adam's sheet: TBD owners, 'All' assignments, unnamed '+' additions, and missing dates.
Nothing has been added, removed, or modified from Adam's original data.
FOR STEVE — Your job this week
1. Read the ICS Dashboard tab first. Every red flag is a gap from Adam's sheet that must be resolved before Monday.
2. Pull Adam's Gantt tab from the Google Sheets roadmap. Populate the Start Date and ETA columns in the RACI tracker for every task.
3. Send the Personal Commitment Cards tab to each team member. Ask them to fill columns E, F, G for every task they are listed as owner on.
4. Collect all responses. Flag every task where the answer is No or Partial. Bring the flagged list to Monday's meeting.
5. Do NOT try to resolve the gaps yourself before Monday. Surface them. Let the team resolve them in the Planning Meeting.
FOR ALL TEAM MEMBERS
Go to the Personal Commitment Cards tab. Find your section.
Column E: Can you commit? YES / NO / PARTIAL.
Column F: Your honest, realistic date — not optimistic, not what Taylor wants to hear. What you can actually deliver.
Column G: What do you need from others before you can start? Be specific.
Return your section to Steve before Friday EOD.
RACI LEGEND
R = Responsible: The person who does the actual work. Every task must have exactly one R.
A = Accountable: Owns the outcome. Taylor as IC is A on all tasks.
A/R = Both accountable and doing the work (applies to Taylor on shared tasks).
C = Consulted: Their input is needed. Two-way communication.
I = Informed: Kept up to date. One-way communication.
ICS Rule: One R per task. Multiple R owners = zero accountability.

## Taylor notes
Topic 1 — Campaign Costs and Accountability | This is Adam's lane. He will brief the campaigns. What you need to walk in with is a budget number — or a budget range — that you have actually approved in your head. The question to answer before Monday: What is the total marketing budget for the launch period — pre-launch through 90 days post-launch? Not what you hope to spend. What you can actually commit to spending without it threatening the company's survival if the first campaigns underperform. Adam needs a ceiling. Without it he cannot build campaigns that are financially responsible. He will build to whatever the vision requires — and the vision is always more expensive than the budget. Give him a number. Even a range. That is the most useful thing you can do before Monday.
Topic 2 — Customer Success Infrastructure | Adam is right that this needs a plan before the first user arrives. Here is the honest answer for a company at your stage. Before X clients — Steve owns customer success as part of his operations role. He is already tracking workstreams and communication. Add a simple process: one inbox, one response SLA, one weekly review of complaints and bugs routed to Hammad. The X where you hire a dedicated person — industry standard for an app at your price point and complexity is somewhere between 200 and 500 active paying users. When support tickets are taking more than 10 hours a week of Steve's time — you hire. Not before. What you need Monday: agree on the threshold number and the interim process. Steve should walk out of Monday owning the CS workflow until that threshold is hit.
Topic 3 — PMF With a Kill Switch | Adam's instinct here is exactly right and it is rare for a marketing person to say it out loud. Most people avoid the kill switch conversation because it feels like doubt. Adam is raising it because it is discipline. The kill criteria Adam already proposed: if beta, hooks, and First Strike rate are not hitting thresholds by June 8 — delay four weeks. What is not yet defined: the actual thresholds. What number constitutes a passing First Strike rate? What retention metric in the first 14 days tells you the product is working? What percentage of beta users need to say they would be very disappointed if EasyChef Pro went away? That last one is the classic PMF benchmark. Sean Ellis established it — 40% of users saying very disappointed is the threshold for product-market fit. What you need Monday: agree on three specific, measurable KPIs for the June 8 checkpoint. Not general feelings. Numbers with thresholds. Written down. Agreed to by everyone in the room.
Topic 4 — Your Face on Camera | I already flagged this to you privately. Adam built his recommendation on the right instinct but landed on the wrong execution. He said the firefighter origin story is the uncopyable asset. You told me clearly you do not want to be remembered as that firefighter guy. Those are not in conflict. Here is how you reconcile them in Monday's meeting. Tell Adam directly: the story matters. The label does not. You are comfortable on camera. You are comfortable sharing the truth of why you built this. What you are not comfortable with is being positioned as the firefighter founder. You are the founder who spent 31 years watching what happens when people have no system — and built the one that should have always existed. That is the camera angle. That is the brand. The firefighter is context. Not the headline. On the four to five hours commitment: you are already committing five hours a week to writing. Adding four to five hours of camera time on top of that is nine to ten hours of content production weekly. That is before operations, before product decisions, before team management. Be honest with Adam about what is actually sustainable. A founder who burns out two months before launch is not an asset. A founder who shows up consistently for twelve months is everything. My recommendation: commit to two to three hours of camera time per week. One longer piece every two weeks. Short clips cut from conversations and team moments in between. That is sustainable. That builds the library. And it does not require a studio or a production schedule to execute.
Beta starts May 11 — 30 days of real family receipts | This is the most important line in his entire message. He is saying the same thing I have been saying from the content side — we do not market claims. We market outcomes. The beta is not a product test. It is a story collection engine. Every real family that uses EasyChef Pro for 30 days is producing the content that no ad budget can buy. The soccer mom story that Steve told in Session 1 — that is what 30 days of beta produces. Real people. Real meals. Real Tuesday nights that actually worked. That is what converts skeptical moms in Facebook Groups. Not features. Not taglines. Not ads. Adam is protecting the integrity of that story. So am I.
Social prep holds until Week 4 — no content before beta data | This aligns exactly with the playbook. The content calendar I am building does not start the product-related content until there is evidence to back it up. Taylor's personal content — The Foundation newsletter, the building in public posts, the founder's perspective — that starts now. That is not a product claim. That is a human story. But the campaign content. The social proof content. The "this is what better feels like" content that points at the product — that waits for the beta data. Adam is right. Posting claims before we have evidence is not just ineffective. It is a trust problem that cannot be undone.
Onboarding under 3 minutes — the Aha moment ships on time | This is Hammad's lane but it has a direct brand implication. The promise we are making in every piece of content — that EasyChef Pro fits inside real life without adding friction — has to be true the moment someone opens the app. If the onboarding takes 8 minutes and requires 14 decisions before the user sees any value — the brand promise is broken before the product even has a chance. The content I am writing is setting an expectation. The onboarding has to meet it.
The kill criteria — delay four weeks if thresholds are not hit by June 8 | This is the most important strategic decision the team makes in the next 30 days. Not because you expect to hit the kill criteria. Because the existence of the kill criteria is what keeps every decision honest between now and June 8. When the kill criteria is agreed to — nobody can convince themselves that soft beta results are good enough. Nobody can argue that the launch should happen on schedule anyway. The number is the number. The threshold is the threshold. That is Adam's best instinct in this entire thread and it deserves explicit agreement from you as the Incident Commander.
T-039 — Customer Success Infrastructure | Owner: Taylor / Sadee Email Sadee@DGL.dev Status: Ready to deploy Dependencies: Beta launch May 11 I am thinking of just Support@easyChefPro.com Notes: Sadie owns front line. Boho Beach Hut team on standby for surge. Zendesk as ticket system. Dedicated support email and separate alpha/beta feedback channel.
T-040 — Alpha and Beta Feedback Loop | Owner: Adam / Sadie Status: Ready to set up Dependencies: Beta launch May 11 Notes: Separate email channel. Feedback routed to Hammad for bugs, Adam for PMF signals, Mary for user language capture.
The One Thing I Want You To Set Up This Week | Before beta starts May 11 — get the two email addresses created and the Zendesk account live. I will choose Alpha and Beta emails based on names of the campain like "founders" or something That is it. Two email addresses and one Zendesk setup. Sadie can handle the configuration. It takes a few hours. When the first beta user hits a problem on May 12 — the system is already there. Not being built while someone is waiting for a response.
The Threshold for Hiring | Sadie handles up to approximately 30 to 50 tickets per week without it affecting her other responsibilities. When support volume consistently exceeds that threshold — you bring in one of the Boho Beach Hut team members part time. When it exceeds 150 tickets per week consistently — you hire a dedicated CS person.