## Roadmap
# | Workstream | Week | Date Range | Task / Milestone | Detail | Owner | Status
1 | Positioning & Brand | W1 | Apr 20–26 | Lock positioning | Mary kickoff
2 | Positioning & Brand | W2 | Apr 27–May 3 | Brand doc + voice guide
3 | Positioning & Brand | W3 | May 4–10 | Final approval
4 | Positioning & Brand | W4–LAUNCH | May 11–17 → Jun 29–Jul 5 | Brand applied across all assets | Review weekly
5 | Website | W1 | Apr 20–26 | Kickoff + structure | Use Mary's Apr 17 content
6 | Website | W2 | Apr 27–May 3 | Design + wireframes
7 | Website | W3 | May 4–10 | Build (dev sprint)
8 | Website | W4 | May 11–17 | Build cont'd + waitlist signup live
9 | Website | W5 | May 18–24 | QA + content polish
10 | Website | W6 | May 25–31 | Beta-family stories integrated
11 | Website | W7 | Jun 1–7 | Conversion testing
12 | Website | W8 | Jun 8–14 | A/B test hooks on landing
13 | Website | W9 | Jun 15–21 | Hard-launch landing page locked
14 | Website | W10 | Jun 22–28 | Final QA + load test
15 | Website | LAUNCH | Jun 29–Jul 5 | LIVE | Milestone
16 | Customer Discovery (Mom Test) | W1 | Apr 20–26 | 5 interviews | Champions
17 | Customer Discovery (Mom Test) | W2 | Apr 27–May 3 | 5 interviews | Economic Buyers
18 | Customer Discovery (Mom Test) | W3 | May 4–10 | 5 interviews | Health Optimizers
19 | Customer Discovery (Mom Test) | W4 | May 11–17 | Synthesis + JTBD update
20 | Customer Discovery (Mom Test) | W5–LAUNCH | May 18–24 → Jun 29–Jul 5 | Insights feed back into copy, onboarding, ad hooks | Continuous
21 | App Onboarding (EUREKA) | W1 | Apr 20–26 | Map First Strike + bowling alleys
22 | App Onboarding (EUREKA) | W2 | Apr 27–May 3 | Build 3-Ingredient Start flow
23 | App Onboarding (EUREKA) | W3 | May 4–10 | Receipt-scan OCR + Walmart sync
24 | App Onboarding (EUREKA) | W4 | May 11–17 | Spoilage alerts + savings dashboard
25 | App Onboarding (EUREKA) | W5 | May 18–24 | Conversational bumpers (push/email)
26 | App Onboarding (EUREKA) | W6 | May 25–31 | Internal alpha (team)
27 | App Onboarding (EUREKA) | W7 | Jun 1–7 | Beta cohort onboarded
28 | App Onboarding (EUREKA) | W8 | Jun 8–14 | Iterate from beta data
29 | App Onboarding (EUREKA) | W9 | Jun 15–21 | Polish — paywall logic
30 | App Onboarding (EUREKA) | W10 | Jun 22–28 | Final QA — <3 min Aha
31 | App Onboarding (EUREKA) | LAUNCH | Jun 29–Jul 5 | SHIP | Milestone
32 | Email Marketing | W2 | Apr 27–May 3 | Prep kickoff + ESP setup
33 | Email Marketing | W3 | May 4–10 | Waitlist nurture (5 emails)
34 | Email Marketing | W4 | May 11–17 | Beta-recruit sequence
35 | Email Marketing | W5 | May 18–24 | Welcome flow (post-install)
36 | Email Marketing | W6 | May 25–31 | Re-engagement flow
37 | Email Marketing | W7 | Jun 1–7 | Founding-member offer email
38 | Email Marketing | W8 | Jun 8–14 | Test sends (10% sample)
39 | Email Marketing | W9 | Jun 15–21 | Launch-week countdown sequence
40 | Email Marketing | W10 | Jun 22–28 | Scheduled and queued
41 | Email Marketing | LAUNCH | Jun 29–Jul 5 | SEND | Milestone
42 | Beta (50 Real Families) | W1 | Apr 20–26 | Define recruit criteria + screening
43 | Beta (50 Real Families) | W2 | Apr 27–May 3 | Open application via waitlist
44 | Beta (50 Real Families) | W3 | May 4–10 | Select 50 families | Walmart-shopper zips
45 | Beta (50 Real Families) | W4 | May 11–17 | Concierge onboarding (Flintstone)
46 | Beta (50 Real Families) | W5 | May 18–24 | Week 1 receipts + check-ins
47 | Beta (50 Real Families) | W6 | May 25–31 | Week 2 — 1st spoilage saves
48 | Beta (50 Real Families) | W7 | Jun 1–7 | Week 3 — savings counters
49 | Beta (50 Real Families) | W8 | Jun 8–14 | Week 4 — case studies drafted
50 | Beta (50 Real Families) | W9 | Jun 15–21 | Testimonials + receipts published
51 | Beta (50 Real Families) | W10 | Jun 22–28 | App store reviews seeded (Day 1)
52 | Beta (50 Real Families) | LAUNCH | Jun 29–Jul 5 | PROOF LIVE | Milestone
53 | Social Media | W4 | May 11–17 | Prep: 10 hooks + studio + handles
54 | Social Media | W5 | May 18–24 | Batch shoot (90 micro-content)
55 | Social Media | W6 | May 25–31 | Int'l hook tests ($1.5K)
56 | Social Media | W7 | Jun 1–7 | Identify winning hooks → 10×
57 | Social Media | W8 | Jun 8–14 | Engagement group active daily
58 | Social Media | W9 | Jun 15–21 | ORGANIC GO-LIVE | jab : hook = 7:1
59 | Social Media | W10 | Jun 22–28 | Power likes + Pinterest blitz
60 | Social Media | LAUNCH | Jun 29–Jul 5 | RIGHT HOOK | Milestone
61 | Influencers & Alliances | W2 | Apr 27–May 3 | Map 50 mom-creators + 5 RDs
62 | Influencers & Alliances | W3 | May 4–10 | Outreach + relationship building
63 | Influencers & Alliances | W4 | May 11–17 | Sign 15 mid-tier creators
64 | Influencers & Alliances | W5 | May 18–24 | Brief + ship product to creators
65 | Influencers & Alliances | W6 | May 25–31 | 30-day documented experiments begin
66 | Influencers & Alliances | W7 | Jun 1–7 | First receipt-reveal posts
67 | Influencers & Alliances | W8 | Jun 8–14 | RD endorsement videos drop
68 | Influencers & Alliances | W9 | Jun 15–21 | Coordinated launch-week posting
69 | Influencers & Alliances | W10 | Jun 22–28 | Amplify top performers (paid)
70 | Influencers & Alliances | LAUNCH | Jun 29–Jul 5 | SURGE | Milestone
71 | Launch Ops & Infra | W1 | Apr 20–26 | Cloud API engineer onboarding (Hammad)
72 | Launch Ops & Infra | W3 | May 4–10 | Test-net → cloud migration
73 | Launch Ops & Infra | W5 | May 18–24 | Load-test 100K concurrent
74 | Launch Ops & Infra | W7 | Jun 1–7 | App store submission (10-day review)
75 | Launch Ops & Infra | W9 | Jun 15–21 | App approved + monitoring stack
76 | Launch Ops & Infra | W10 | Jun 22–28 | War-room schedule + comms tree
77 | Launch Ops & Infra | LAUNCH | Jun 29–Jul 5 | 2026-07-01 | Public Launch

## Gantt
Workstream | W1 Apr 20–26 | W2 Apr 27–May 3 | W3 May 4–10 | W4 May 11–17 | W5 May 18–24 | W6 May 25–31 | W7 Jun 1–7 | W8 Jun 8–14 | W9 Jun 15–21 | W10 Jun 22–28 | LAUNCH Jun 29–Jul 5
1. Positioning & Brand | Lock positioning | Brand doc + voice guide | Final approval | Brand applied | Brand applied | Brand applied | Brand applied | Brand applied | Brand applied | Brand applied | Brand applied
2. Website | Kickoff + structure | Design + wireframes | Build (dev sprint) | Build + waitlist live | QA + content polish | Beta stories integrated | Conversion testing | A/B test hooks | Landing page locked | Final QA + load test | LIVE
3. Customer Discovery (Mom Test + user journey mapping) | 5 interviews — Champions | 5 interviews — Econ Buyers | 5 interviews — Health Optim. | Synthesis + JTBD update | Insights feedback | Insights feedback | Insights feedback | Insights feedback | Insights feedback | Insights feedback | Insights feedback
4. App Onboarding (EUREKA) | Map First Strike | Build 3-Ingredient Start | Receipt OCR + Walmart | Spoilage alerts + savings | Conversational bumpers | Internal alpha | Beta cohort onboarded | Iterate from beta | Polish — paywall | Final QA <3min Aha | SHIP
5. Email Marketing |  | Prep + ESP setup | Waitlist nurture (5) | Beta-recruit sequence | Welcome flow | Re-engagement flow | Founding-member offer | Test sends (10%) | Countdown sequence | Scheduled + queued | SEND
6. Beta (50 Real Families) | Recruit criteria | Open application | Select 50 families | Concierge onboarding | Week 1 receipts | Week 2 spoilage saves | Week 3 savings | Week 4 case studies | Testimonials published | App store reviews seeded | PROOF LIVE
7. Social Media |  |  |  | Prep: 10 hooks + studio | Batch shoot (90 content) | Int'l hook tests $1.5K | Winning hooks → 10× | Engagement group daily | ORGANIC GO-LIVE | Power likes + Pinterest | RIGHT HOOK
8. Influencers & Alliances |  | Map 50 creators + 5 RDs | Outreach + relationships | Sign 15 mid-tier | Brief + ship product | 30-day experiments begin | Receipt-reveal posts | RD endorsement videos | Launch-week posting | Amplify top (paid) | SURGE
9. Launch Ops & Infra | Hammad onboarding |  | Test-net → cloud |  | Load-test 100K |  | App store submit |  | App approved + monitor | War-room + comms tree | 2026-07-01

## Key Dates
Date | Milestone
Fri Apr 17, 2026 | Mary delivers website content draft
Mon Apr 20, 2026 | Website kickoff + positioning lock + onboarding build starts
Mon Apr 27, 2026 | Email sequences prep begins
Mon May 11, 2026 | Social campaign prep + 50-family beta launches
Mon Jun 15, 2026 | Public social campaign goes live
Wed Jul 1, 2026 | Public Launch

## Critical Callouts
Callout | Detail
THE CRITICAL DEPENDENCY | The 50-family beta MUST start by May 11 (W4). Their 30 days of documented receipts produce the social proof that powers the social campaign (W9), website testimonials (W6), email sequences (W7), and app store reviews on launch day. Slip the beta = slip the entire launch.
THE CONTENT ENGINE STARTS LATE | Social media prep doesn't begin until W4 (May 11) — a deliberate choice. We need beta data first or we're posting marketing claims, not real outcomes. Once the engine starts: 90 micro-content pieces/week, hypothesize-test-pivot weekly, shares as the only KPI.
DO NOT SLIP ONBOARDING | The <3-minute Three-Ingredient Start is the conversion lever for every dollar spent on social, email, and influencers. If onboarding ships with friction, every other workstream wastes its budget. App must be in beta hands by W4.
RUNNING METRICS | Weekly review every Friday: (1) website conversion, (2) waitlist growth, (3) Day-7 First Strike rate (beta), (4) social share rate, (5) email open + click. Anything below threshold gets killed or fixed within 7 days.
FOUNDER ON CAMERA — NON-NEGOTIABLE | Taylor + Steve must commit to 4 hours of filming per month starting W2. Firefighter origin story is the uncopyable brand asset across website, social, YouTube, and influencer co-creation. Without their face on camera, we are just another meal app.
KILL CRITERIA BEFORE JULY 1 | If by W8 (Jun 8): (a) <30 beta families have completed 30 days of logged receipts, OR (b) <5 hooks have hit 5%+ share rate in tests, OR (c) onboarding First Strike <40% — delay launch by 4 weeks and fix.