## Task Tracker
Task ID | Task Name | Category | Priority | Status | Owner | Start Date | ETA | Dependencies | Notes / Description
T-001 | ICP Research | Marketing Strategy | High | Started | Adam |  |  |  | Define ideal customer profile: demographics, psychographics, pain points
T-002 | Competitive Analysis | Marketing Strategy | High | Started | Adam |  |  |  | Map direct & indirect competitors; feature/pricing/positioning matrix
T-003 | Positioning Strategy | Marketing Strategy | High | Started | Adam |  |  | T-001, T-002 | Craft market position statement; own-able whitespace
T-004 | Differentiation | Marketing Strategy | High | Started | Adam |  |  | T-003 | Define key differentiators vs. alternatives
T-005 | Brand Messaging Framework / Tagline | Marketing Strategy | High | Started | Adam |  |  | T-003 | Value prop, tone of voice, messaging pillars, tagline
T-006 | Pricing | Marketing Strategy | High | Started | Adam |  |  | T-001, T-002 | Freemium vs. paid tiers; willingness-to-pay research
T-007 | Behavioural Economics Analysis | Marketing Strategy | Medium | Started | Adam |  |  | T-001 | Anchoring, loss aversion, social proof levers to embed in UX & copy
T-008 | Go-to-Market (GTM) Strategy | Marketing Strategy | High | Started | Adam |  |  | T-003, T-006 | Master launch plan: channels, sequencing, budget allocation, KPIs
T-009 | Customer Journey Mapping (Full-Funnel) | Marketing Strategy | High | Started | Adam |  |  | T-001, T-003 | Awareness > activation > retention > referral journey
T-010 | Brand Guidelines & Visual Identity | Brand | High | Not Started | Adam |  |  | T-005 | Logo, colour palette, typography, imagery style, icon system
T-011 | Website Content (all pages) | Content - Website | High | Not Started | Adam |  |  | T-005, T-010 | Homepage, features, pricing, about, blog index
T-012 | Website Pre-Launch Content | Content - Website | High | Started | Mary |  |  | T-011 | Coming-soon page, waitlist CTA, teaser messaging
T-013 | Video Demo / Explainer Content | Content - Website | High | Not Started | Adam + |  |  | T-005, T-010 | 60-90s product demo for homepage and social ads
T-014 | App Store Listing (ASO Copy) | Content - Website | High | Not Started | Hammad |  |  | T-005 | Title, subtitle, description, keywords; App Store & Google Play
T-015 | Blog / Content Strategy | Content - Website | Medium | Not Started | Mary + Adam |  |  | T-003 | Editorial calendar; SEO-led topics that build authority
T-016 | PR / Press Outreach Strategy | Content - Website | Medium | Not Started | Mary + Adam |  |  | T-008 | Target media list, story angles, press kit
T-017 | Search Engine Optimization (SEO) | Digital Marketing | High | Not Started | Adam |  |  | T-011 | On-page, technical SEO, backlink strategy
T-018 | Paid Search (SEM / Google Ads) | Digital Marketing | High | Not Started | Adam + |  |  | T-008 | Keyword strategy, ad copy, landing pages, bidding
T-019 | App Store Ads (Apple Search Ads / UAC) | Digital Marketing | High | Not Started | Adam + |  |  | T-014, T-008 | ASA and Google UAC campaign setup
T-020 | Influencer Marketing | Digital Marketing | Medium | Not Started | JR |  |  | T-008, T-010 | Identify micro/macro food creators; brief and contract
T-021 | Retargeting Campaign Setup | Digital Marketing | High | Not Started | Adam + |  |  | T-018 | Pixel setup, audience lists, retargeting ad creative briefs
T-022 | Social Media Campaign Design | Social Media Marketing | High | Not Started | Adam + |  |  | T-008, T-010 | Platform strategy (IG, TikTok, Pinterest); content calendar
T-023 | Advertising Budget & User Journey Mapping | Social Media Marketing | High | Not Started | Taylor + Steve + Adam |  |  | T-008, T-009 | Paid social budget split; map ad touchpoints to funnel stages
T-024 | Social Media Creatives | Social Media Marketing | High | Not Started | Adam + |  |  | T-010, T-022 | Static, carousel, Reel/TikTok creative assets
T-025 | Email Marketing Campaign | Email Marketing | High | Not Started | JR + Mary |  |  | T-008 | Broadcast campaigns: promos, feature announcements, newsletters
T-026 | Onboarding Email Sequence | Email Marketing | High | Not Started | JR |  |  | T-009, T-025 | Welcome > activation drip (Day 0-14); drive first recipe use
T-027 | Product-Led Onboarding | Product Marketing | High | Started | Adam + Hammad + Taylor + Steve |  |  | T-009 | In-app onboarding flows that drive time-to-value
T-028 | User Story Cards | Product Marketing | High | Started | Adam |  |  | T-001 | Backlog of user stories prioritised for launch sprint
T-029 | Cold Start Tactics | Product Marketing | High | Started | Adam |  |  | T-008 | Bootstrapping initial users: communities, waitlist, beta program
T-030 | Referral Program Design | Product Marketing | High | Not Started | JR |  |  | T-029 | Incentive structure, referral mechanics, tracking
T-031 | In-App Notification Strategy | Product Marketing | Medium | Not Started | Hammad + Adam |  |  | T-027 | Push / in-app messages to drive retention and feature discovery
T-032 | Feature Launch Announcement Strategy | Product Marketing | Medium | Not Started | All |  |  | T-005 | Template and process for communicating new features post-launch
T-033 | A/B Testing Framework Setup | Data Science | High | Not Started | Hammad + Adam |  |  |  | Define test methodology, tooling, statistical significance thresholds
T-034 | Funnel Analysis & Conversion Tracking | Data Science | High | Not Started | Hammad + Adam |  |  | T-027 | Event tracking; map funnel from install to paid; identify drop-offs
T-035 | App Analytics | Data Science | High | Not Started | Hammad + Adam |  |  | T-034 | DAU/MAU, retention curves, feature engagement; dashboard setup
T-036 | Website Analytics | Data Science | High | Not Started | Hammad + Adam |  |  |  | GA4 / Mixpanel setup; goals, events, attribution model
T-037 | Retention & Churn Analysis Framework | Data Science | Medium | Not Started | Hammad + Adam |  |  | T-035 | Cohort retention analysis; churn signals; lifecycle segmentation
T-038 | Food Creator / Influencer Partnership Program | Partnerships | Medium | Not Started | TBD |  |  | T-020 | Long-term ambassador tiers, content obligations, compensation model

## Summary
Tasks by Category
Category | Total Tasks | % of Backlog | Legend
Brand | 1 | #DIV/0!
Content - Website | 6 | #DIV/0!
Data Science | 5 | #DIV/0!
Digital Marketing | 5 | #DIV/0!
Email Marketing | 2 | #DIV/0!
Marketing Strategy | 9 | #DIV/0!
Partnerships | 1 | #DIV/0!
Product Marketing | 6 | #DIV/0!
Social Media Marketing | 3 | #DIV/0!
Status Key
Not Started
In Progress
In Review
Completed
Blocked
Priority Key
High
Medium
Low